## Schedule
Task | Team Member | Due Date | Completion
Initial Research | Everyone | 2023-01-23 | Done
Preliminary Research | Everyone | 2023-01-23 | Done
Frame Problem | Everyone | 2023-02-03 | Done
Individual Design Dossier 1 Components | Everyone | 2023-02-15 | Done
Group Design Dossier 1 Components | Everyone | 2023-02-16 | Done
CAD Beakers/Baskets | Everyone | 2023-03-14 | Done
CAD Box | Yang | 2023-03-14 | Done
Print Beakers/Baskets version 1.0 | Liam | 2023-03-16 | Done
Laser Cut Box version 1.0 | Yang | 2023-03-16 | Done
Figure out Stepper Motor (Hardware and Software) | Eugene and Joaquin | 2023-03-16 | Done
Asses Prototype Version 1.0 | Yang, Liam, Joaquin | 2023-03-16 | Done
Edit/Update CADs for Prototype 1.0 | Liam, Gerry, Joaquin, Yang | 2023-03-18 | Done
Print/Laser cut version 2.0 Prototype | Liam, Gerry, Joaquin, Yang | 2023-03-19 | Done
Assemble Prototype 2.0 Completely | Liam, Gerry, Yang | 2023-03-30 | Done
Test Prototype 2.0 | Liam, Gerry, Yang | 2023-03-30 | Done
Install Motors to Prototype | Eugene and Joaquin | 2023-03-31 | Done
Figure out DD2 and assign roles | Everyone | 2023-04-03 | Done
Finish assigned DD2 roles | Everyone | 2023-04-06 | Done

## Responsiblity Tracker
Team Member: | Joaquin |  | Team Member: | Yang |  | Team Member: | Gerry |  | Team Member: | Liam |  | Team Member: | Eugene
Task: | Completion | Notes | Task: | Completion | Notes | Task: | Completion | Notes | Task: | Completion | Notes | Task: | Completion | Notes
Design Dossier 1 |  |  | Design Dossier 1 |  |  | Design Dossier 1 |  |  | Design Dossier 1 |  |  | Design Dossier 1
Design Dossier 1: Approaches to Providing Value | Done |  | Design Dossier 1: Conceptual Design | Done |  | Design Dossier 1: Value Proposition | Done |  | Design Dossier 1: Value Proposition | Done |  | Design Dossier 1: Approaches to Providing Value | Done
Design Dossier 1: Statement of Collaboration | Done |  | Design Dossier 1: High-Fidelity Prototype | Done |  | Design Dossier 1: High-Fidelity Prototype | Done |  | Design Dossier 1: Approaches to Providing Value | Done |  | Design Dossier 1: Conceptual Design | Done
Integrate Collab statements with Team Charter | Done |  | Research Microscopy | Done |  | Initial Research:Why are RDTs not available? | Done |  | Initial Research: Research Microscope, hematology analyzer, chemistry analyzer, urinalysis machine, Glucometer | Done |  | Initial Research: Research Microscope Field | Done
Initial Research: Research Re-using RDTs | Done
Design Dossier 2 |  |  | Design Dossier 2 |  |  | Design Dossier 2 |  |  | Design Dossier 2 |  |  | Design Dossier 2
Email Prof. Stickel for resources in Electromagnetism | Done |  | Design sub-components | Done |  | Design sub-components | Done |  | Design sub-components | Done |  | Work on Electronic/Code aspects of design | Done
CAD Beakers/Baskets | Done |  | Design CAD of RTS | Done |  | Design CAD for VTS | Done |  | Print CAD of Beakers and Baskets 1.0 | Done |  | Write part of code with Joaquin | Done
Write part of code with Eugene | Done |  | Design CAD of Base Box | Done |  | Assemble VTS for Prototype 1.0 | Done |  | Budget and 3D Print List | Done |  | Figure out A4988 Motor Driver and two motors for prototype | Done
Figure out A4988 Motor Driver and two motors for prototype | Done |  | Assemble Arm + Box (Protoype 1.0) | Done |  | Assess Prototype 1.0 for needed changes | Done |  | CAD Geneva Gear | Done |  | Integrate motors/breadboard with prototype | Done
Integrate motors/breadboard with prototype | Done |  | Assess Prototype 1.0 for needed changes | Done |  | Assemble Prototype 2.0 | Done |  | Print Arm 0.1 and Laser cut Base Box | Done |  | Test and Debug code | Done
Test and Debug code | Done |  | Update CAD files for changes | Done |  | Test Prototype 2.0 | Done |  | Print Arm 1.0 and VTS and RTS | Done |  | DD2 Assignment | Done
Test Prototype 2.0 | Done |  | Assemble Prototype 2.0 | Done |  | DD2 Assignment | Done |  | Assemble Prototype 1.0 | Done
DD2 Assignment | Done |  | Test Prototype 2.0 | Done |  | your mom | Done |  | Asses Prototype 1.0 for needed changes | Done
|  |  | DD2 Assignment | Done |  |  |  |  | Print Prototype 2.0 parts | Done
[9 empty] | Assemble Prototype 2.0 | Done
[9 empty] | DD2 Assignment | Done

## Dossier 2 To-do-list
Dossier 2 Task: | Due Date | Who is responsible | Green is complete, Yellow is in-transit, red is DANGER DANGER DANGER
Sub-Component Descriptions | 2023-04-03 | Yang, Gerry, Joaquin, Eugene
Upload Artifacts and Update the list in Interactive Summary | 2023-04-04 | Joaquin, Yang and/or Liam
Update Responsiblity Tracker | 2023-04-04 | Joaquin and Liam
Write updated Statement of Collaboration | 2023-04-04 | Liam + Yang/Gerry
Edit Design Dossier 1 1 stuff | 2023-04-06 | Everyone
Timeline | 2023-04-04 | Liam and Eugene
Figure out why the TA couldn't find certain files | 2023-04-04 | Joaquin
Note on A3: Do before editing Design Dossier 1 -Joaquin Arcilla
Note on A7: Check discord -Joaquin Arcilla

## Budget Tracker
Part | Number | Cost | Total Cost | Order Date | Status | Notes
Stepper motor driver A4988 | 1 | 2.12 | 2.12 | 2023-03-20 | Collected | Ord-14774
Stepper motor driver A4988 | 1 | 2.12 | 2.12 | 2023-03-24 | Collected | Ord-15033
Stepper motor Nema 17 | 1 | 6.47 | 6.47 | 2023-03-25 | Collected | Ord-15033
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 3D Print list
Part | Number | Cost | Total Cost | Order Date | Order # | Printer | Material | Status | Date Ready
Geneva Mechanism | 1 | 2.31 |  | 2023-03-03 | 3D-4201 | 3D Printer - Mini | 3D - PLA | Collected | 2023-03-04
Box Laser Cut | 2 | 4.26 |  | 2023-03-14 | Las-4349 | Laser Cutter | Plywood 3 mm | Collected | 2023-03-17
Beaker | 3 | 2.49 |  | 2023-03-15 | 3D-4350 | 3D Printer - Mini | 3D-PLA | Collected | 2023-03-17
Arm | 4 | 6.75 |  | 2023-03-15 | 3D-4379 | 3D Printer - Mk3 | 3D-PLA | Collected | 2023-03-18
washers and gears | 5 | 4.2 |  | 2023-03-19 | 3D-4502 | 3D Printer - Mini | 3D-PLA | Collected | 2023-03-20
print gears and doodads | 6 | 0 |  | 2023-03-20 | 3D-4543 | 3D Printer - Mini | 3D-PLA | Rejected
print arm v1 | 7 | 3.96 |  | 2023-03-20 | 3D-4544 | 3D Printer - Mini | 3D-PLA | Collected | 2023-03-23
print gears and doodads v3.3 | 8 | 1.08 |  | 2023-03-22 | 3D-4591 | 3D Printer - Mini | 3D-PLA | Collected
boxlayout | 9 | 8.52 |  | 2023-03-26 | Las-4675 | Laser Cutter | Plywood 3 mm | Collected | 2023-03-28
boxlayout | 10 | 8.52 |  | 2023-03-26 | Las-4676 | Laser Cutter | Plywood 3 mm | Collected | 2023-03-28
Geneva Mechanism and Lids | 11 | 2.37 |  | 2023-03-26 | 3D-4677 | 3D Printer - Mk3 | 3D-PLA | Collected | 2023-03-28
Beakers | 12 | 0 |  | 2023-03-26 | 3D-4678 | 3D Printer - Mk3 | 3D-PLA | Rejected
boxlayout | 13 | 8.52 |  | 2023-03-26 | Las-4686 | Laser Cutter | Plywood 3 mm | Collected | 2023-03-28
boxlayout | 14 | 8.52 |  | 2023-03-26 | Las-4687 | Laser Cutter | Plywood 3 mm | Collected | 2023-03-28
Beakers v6 | 16 | 14.82 |  | 2023-03-27 | 3D-4697 | 3D Printer - Mk3 | 3D-PLA | Collected | 2023-03-30
print arm part 2 v2 | 17 | 0.18 |  | 2023-03-28 | 3D-4721 | 3D Printer - Mini | 3D-PLA | Collected | 2023-03-28
Magnets | 18 | 0
76.5